## RapidPro Flow UI(Prototype & Wi
Tracking ID | Module/Sub Module/Feature | Build Version/URL | Testing Date | Issue Findings (Issue name, Steps to reproduce, Actual Result, Expected Result, Test Data) | Issue Category | Issue Type | Priority | QA Status | QA Name | Attachment | QA Remarks | Reporting Manager's Feedback | Current Iteration | Issue Occurance Count | Developer Name | Issue Status-Developers Feedback | Developer's Remark | Defect Solved Date
TC_001 | Prototype Page (Row 1, Column 1) |  | 2023-03-07 | Issue: "Create New" button is not matched. | Fine Tuning | GUI Error | High | Open | Ridwan |  | It should be the same as Wireframe's "Create Flow".
TC_002 | Prototype Page (Row 1, Column 1) |  | 2023-03-07 | Issue: In the prototype there has a search icon | Fine Tuning | GUI Error | High | Open | Ridwan |  | There should not be any search icon.
TC_003 | Prototype Page (Row 1, Column 1) |  | 2023-03-07 | Issue: In the prototype there shows the profile name | Fine Tuning | GUI Error | High | Open | Ridwan |  | There should not be any Profile Name.
TC_004 | Prototype Page (Row 1, Column 1) |  | 2023-03-07 | Issue: "Rapidpro Flow" button name is not matching with the wireframe. In the wireframe it is just only "RapidPro" | Fine Tuning | GUI Error | Low | Open | Ridwan
TC_005 | Prototype Page (Row 1, Column 1) |  | 2023-03-07 | Issue: Dropdown symbol is missing beside IoGT Translate button. | Fine Tuning | GUI Error | Medium | Open | Ridwan
TC_006 | Prototype Page (Row 1, Column 1) |  | 2023-03-07 | Issue: Log out buttons position is not specified in the wireframe. but in the protype we can see its position is in menu bar. | Fine Tuning | GUI Error | Low | Open | Ridwan
TC_007 | Prototype Page (Row 1, Column 2) |  | 2023-03-07 | Issue: "Create File" modal page background is different from the "Row 1, Column 2" page. | Fine Tuning | GUI Error | High | Open | Ridwan |  | Its background should be the same as the "Row 1, Column 2" page.
TC_008 | Prototype Page (Row 1, Column 3) |  | 2023-03-07 | Issue: "Question" title is not present. | Fine Tuning | GUI Error | High | Open | Ridwan
TC_009 | Prototype Page (Row 1, Column 3) |  | 2023-03-07 | Issue: No padding between "Question number" & "Question Subtitle" | Fine Tuning | GUI Error | High | Open | Ridwan
TC_010 | Prototype Page (Row 1, Column 3) |  | 2023-03-07 | Issue: After clicking "Add Question" for the first time, the "Cancel" & "Add" button is not showing. | Fine Tuning | GUI Error | High | Open | Ridwan
TC_011 | Prototype Page (Row 2, Column 4) |  | 2023-03-07 | Issue: "If not match ans go to" sentence is grammarly incorrect. it would be more user friendly If It says, "If answer don't match, Go to" | Fine Tuning | GUI Error | Medium | Open | Ridwan
TC_012 | Prototype Page (Row 2, Column 5) |  | 2023-03-07 | Issue: After creating a "Multiple Question", the "Multiple Choice" field is still showing. | Fine Tuning | GUI Error | High | Open | Ridwan
TC_013 | Prototype Page (Row 2, Column 7) |  | 2023-03-07 | Issue: In some question titles, it is showing "Question 1". But it should show "Question" only. | Fine Tuning | GUI Error | High | Open | Ridwan
TC_014 | Prototype Page (Row 3, Column 6) |  | 2023-03-07 | Issue: In the "3.1 Question" Response for the select dropdown, 3(f) is not showing. | Fine Tuning | GUI Error | High | Open | Ridwan
TC_015 | Prototype Page (Row 3, Column 6) |  | 2023-03-07 | Issue: Dropdown symbol is missing beside "Multiple choice" button. | Fine Tuning | GUI Error | Medium | Open | Ridwan
TC_016 | Prototype Page (Row 3, Column 8) |  | 2023-03-07 | Issue: In "3.1 Question" the "Response for" is showing "2(b)". | Fine Tuning | GUI Error | High | Open | Ridwan |  | It should shows "3(f)"
TC_017 | Prototype Page (Row 3, Column 8) |  | 2023-03-07 | Issue: Question alignment is not matching with wireframe. | Fine Tuning | GUI Error | Medium | Open | Ridwan
TC_018 | Prototype Page (Row 3, Column 9) |  | 2023-03-07 | Issue: In the "3.2 Question" in the "Response for select" dropdown, the "3.1 Question" is selected. | Fine Tuning | GUI Error | High | Open | Ridwan |  | It should select "Question 3"
TC_019 | Prototype Page (Row 3, Column 9) |  | 2023-03-07 | Issue: There is a dropdown beside Input box field which is given in the prototype. But it is not given in the wireframe. | Fine Tuning | GUI Error | Medium | Open | Ridwan
TC_020 | Prototype Page |  | 2023-03-07 | Issue: All button Text is too small | Fine Tuning | GUI Error | High | Open | Ridwan
TC_021 | Prototype Page |  | 2023-03-07 | Issue: Last 3 page from the wireframe is not present on the prototype page. | Fine Tuning | GUI Error | High | Open | Ridwan