## UI Issues
Tracking ID | Module/Sub Module/Feature | Build Version/URL | Testing Date | Issue Findings (Issue name, Steps to reproduce, Actual Result, Expected Result, Test Data) | Issue Category | Issue Type | Priority | QA Status | QA Name | Attachment | QA Remarks | Reporting Manager's Feedback | Current Iteration | Issue Occurance Count | Developer Name | Issue Status-Developers Feedback | Developer's Remark | Defect Solved Date
TC_001 | Login |  | 2023-02-01 | Issue: Login Screen Password field has no Eye Icon (as per Figma Design) STR: 1. Go to the URL 2. Login Screen Appears. | Fine Tuning | GUI Error | Low | Solved | Ridwan | [5 empty] | Amirul | Solved |  | 2023-02-02
TC_002 | Login |  | 2023-02-01 | Issue: Login Screen Box has extra gap between Login Button (as per figma Design) STR: 1. Go to the URL 2. Login Screen Appears. | Fine Tuning | GUI Error | Medium | Open | Ridwan | [5 empty] | Amirul | Solved
TC_003 | Login > Forgot Password |  | 2023-01-31 | Issue: Too much Void/Margin before & after the inputbox STR: 1. Go to the URL 2. Click on Forgot Password | Fine Tuning | GUI Error | Medium | Open | Ridwan | [5 empty] | Amirul | Solved
TC_004 | Login > Forgot Password |  | 2023-01-31 | Issue: The error message is not standard looking in the forgot password section. STR: 1. Go to the URL 2. Click on Forgot Password | Fine Tuning | GUI Error | Medium | Open | Ridwan |  | The error message should be shown below the Inputbox with red color text without any background color. |  |  |  | Amirul | Solved
TC_005 | Login > Forgot Password |  | 2023-01-31 | Issue: After login the "Welcome" loading screen is not showing. It redirected to the dashboard instantly. But in Figma file there has a Welcome Loading Screen page design. STR: 1. Go to the URL 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 | Fine Tuning | GUI Error | High | Solved | Ridwan | [5 empty] | Amirul | Solved
TC_006 | Reset Password |  | 2023-01-31 | Issue: Not showing User friendly error message if the user try email that doesn't have any account. STR: 1. Go to the URL 2. Click on Forgot Password 3. Input any email id that is not incorporated with any Account. 4. Click Reset and check error message. | Fine Tuning | Error Handling Errors | Medium | Solved | Ridwan | [5 empty] | Amirul | Solved
TC_007 | Dashboard |  | 2023-01-31 | Issue: In the dashboard body section, all contents has low left-margin from the menu bar. STR: 1. Go to the URL 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 | Fine Tuning | GUI Error | Medium | Open | Ridwan |  | In the figma file the left-margin is given 57px. |  |  |  | Amirul | Solved
TC_008 | Dashboard > Cards |  | 2023-01-31 | Issue: In the dashboard body section, all cards width is too high. STR: 1. Go to the URL 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 | Fine Tuning | GUI Error | Medium | Open | Ridwan |  | In the figma file: Width: 444px Height: 249px |  |  |  | Amirul | Solved
TC_009 | Dashboard > Cards |  | 2023-01-31 | Issue: In the dashboard cards, "The Number" & "Title" texts size & width is not matched with Figma Design. STR: 1. Go to the URL 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 | Fine Tuning | GUI Error | Medium | Open | Ridwan |  | In the figma file: Number Size: 72px/4.5rem & Width: 700. Title size: 24px/1.5rem & Width: 600 |  |  |  | Amirul | Solved
TC_010 | Dashboard > Profile Icon |  | 2023-01-31 | Issue: In the dashboard, The Profile Icon size small. STR: 1. Go to the URL 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 | Fine Tuning | GUI Error | Medium | Solved | Ridwan |  | In the figma file: The Icon width: 48.37px; height: 48.37px; |  |  |  | Amirul | Solved
TC_011 | Dashboard > Menu Bar |  | 2023-01-31 | Issue: In the menu bar, "RapidPro" icon is similar with "Dashboard Icon". STR: 1. Go to the URL 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 | Fine Tuning | GUI Error | High | Solved | Ridwan | [5 empty] | Amirul | Solved
TC_012 | File Report > Regions |  | 2023-01-31 | Issue: In the Regions, All cards size is not same. This isn't looking good. STR: 1. Go to the URL 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 3. Click File Report. 4. Click Regions | Fine Tuning | GUI Error | Medium | Open | Ridwan
TC_013 | File Report > Regions |  | 2023-01-31 | Issue: In the Menu Bar, Regions sub module's active color has no margin from File Report modules. STR: 1. Go to the URL 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 3. Click File Report. 4. Click Regions | Fine Tuning | GUI Error | Medium | Open | Ridwan | [5 empty] | Amirul | Solved
TC_014 | File Report > Regions |  | 2023-01-31 | Issue: In Regions Card's, "The Number" & ""Title" texts size & width is not matched with Figma Design. STR: 1. Go to the URL 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 3. Click File Report. 4. Click Regions | Fine Tuning | GUI Error | Medium | Open | Ridwan |  | In the figma file: Number Size: 72px/4.5rem & Width: 700. Title size: 24px/1.5rem & Width: 600
TC_015 | File Report > Rapid Pro |  | 2023-01-31 | Issue: Whole page is not matching with figma file. Also there has no Edit or Delete option like shown in the figma file. STR: 1. Go to the URL 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 3. Click File Report. 4. Click Rapid Pro | Fine Tuning | GUI Error | High | Open | Ridwan |  | In the table there should be Edit & Delete option. |  |  |  | Amirul | Solved
TC_016 | File Report > IoGT |  | 2023-01-31 | Issue: Same issues like Rapid Pro page. Also Search bar & Filter btn is missing. STR: 1. Go to the URL 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 3. Click File Report. 4. Click IoCT. | Fine Tuning | GUI Error | High | Open | Ridwan |  | Should follow the Figma Design properly. |  |  |  | Amirul | Solved
TC_017 | File Report > IoGT |  | 2023-01-31 | Issue: The Tab Title of the IoGT page is wrong. STR: 1. Go to the URL 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 3. Click File Report. 4. Click IoCT. | Fine Tuning | GUI Error | High | Open | Ridwan
TC_018 | User > Admin |  | 2023-01-31 | Issue: Whole page is not matching with figma file. STR: 1. Go to the URL 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 3. Click USer. 4. Click Admin. | Fine Tuning | GUI Error | High | Open | Ridwan |  | Should follow the Figma Design properly. |  |  |  | Amirul | Solved
TC_019 | User |  | 2023-01-31 | Issue: 3 dots menu is clicked on User List, the menu is somehow out of visibility. STR: 1. Go to the URL and login with Editor. 2. Use the credential to login: email: abir.riseuplabs@gmail.com password: 12345678 3. Click on User List 4. Click on 3 Dot menu | Fine Tuning | GUI Error | Low | Solved | Ridwan | [5 empty] | Amirul | Solved
TC_020 | User > Admin |  | 2023-01-31 | Issue: There has no filter btn. STR: 1. Go to the URL 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 3. Click USer. 4. Click Admin. | Fine Tuning | GUI Error | High | Open | Ridwan |  | Should follow the Figma Design properly. |  |  |  | Amirul | Solved
TC_021 | User > Admin > Add Admin |  | 2023-01-31 | Issue: In the Add Admin, the error message is not user friendly & looking odd. STR: 1. Go to the URL 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 3. Click USer. 4. Click Admin. 5. Click Add Admin. | Fine Tuning | GUI Error | Medium | Open | Ridwan |  | The error message should be shown below the Inputbox with red color text without any background color. |  |  |  | Amirul | Solved
TC_022 | User > Editor |  | 2023-01-31 | Issue: Whole page is not matching with figma file. STR: 1. Go to the URL 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 3. Click User. 4. Click Editor. | Fine Tuning | GUI Error | High | Open | Ridwan |  | Should follow the Figma Design properly.
TC_023 | User > Editor |  | 2023-01-31 | Issue: There has no Search bar & filter btn. STR: 1. Go to the URL 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 3. Click User. 4. Click Editor. | Fine Tuning | GUI Error | High | Open | Ridwan |  | Should follow the Figma Design properly.
TC_024 | User > Editor |  | 2023-01-31 | Issue: In the table after click the 3dots, the edit/delete modal is geting out of frame. STR: 1. Go to the URL 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 3. Click User. 4. Click Editor. 5. Click 3dots in table. | Fine Tuning | GUI Error | High | Open | Ridwan |  | The modal can be open in right side.
TC_025 | User > Admin User > Editor |  | 2023-02-01 | Issue: Headers on Admin and Editor are not same. STR: 1. Go to the URL and login with Editor. 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 3. Click on User 4. Click on Admin AND 5. Click on Editor. | Fine Tuning | GUI Error | Low | Open | Ridwan | [5 empty] | Amirul | Not Solved
TC_026 | Dashboard |  | 2023-02-01 | Issue: Dashboard's Box icons are not matching with Figma. STR: 1. Go to the URL and login with Editor. 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 3. Dashboard | Fine Tuning | GUI Error | Low | Open | Ridwan | [5 empty] | Amirul | Not Solved
TC_027 | Dashboard |  | 2023-02-01 | Issue: Dashboard's Box Header text margin and gap between box are not matching with Figma. STR: 1. Go to the URL and login with Editor. 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 3. Dashboard | Fine Tuning | GUI Error | Low | Open | Ridwan | [5 empty] | Amirul | Solved
TC_028 | Dashboard |  | 2023-02-01 | Issue: Dashboard's Box Corner Radius are not fulfilled with Figma. STR: 1. Go to the URL and login with Editor. 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 3. Dashboard | Fine Tuning | GUI Error | Low | Open | Ridwan | [5 empty] | Amirul | Solved
TC_029 | Dashboard > Menu Bar |  | 2023-02-01 | Issue: Dashboard's Box Corner Radius are not fulfilled with Figma. STR: 1. Go to the URL and login with Editor. 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 3. Dashboard | Fine Tuning | GUI Error | Low | Open | Ridwan | [5 empty] | Amirul | Not Solved
TC_030 | Settings |  | 2023-02-01 | Issue: After clicking settings, Profile settings button should be blue and Security button should be white according to figma. STR: 1. Go to the URL and login with Editor. 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 3. Dashboard 4. Click Settings. | Fine Tuning | GUI Error | Low | Open | Ridwan |  | Colors will be viceversa. when profile button is been clicked it should be blue and Security button should be white.. And when Security button is been clicked it should be blue and Profile button should be white.. |  |  |  | Amirul | Solved
TC_031 | Settings > Security settings |  | 2023-02-01 | Issue: After clicking Security settings, Profile settings button should be white and Security button should be blue as per figma design. STR: 1. Go to the URL and login with Editor. 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 3. Dashboard 4. Click Settings. | Fine Tuning | GUI Error | Low | Open | Ridwan | [5 empty] | Amirul | Solved
TC_032 | Settings |  | 2023-02-01 | Issue: In Settings, There is a dropdown symbol which is not needed as per figma design STR: 1. Go to the URL and login with Editor. 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 3. Dashboard 4. Click Settings. | Fine Tuning | GUI Error | Low | Solved | Ridwan | [5 empty] | Amirul | Solved
TC_033 | Settings > Security settings |  | 2023-02-01 | Issue: In Current password field placeholder should be "Old Password" as per Figma design STR: 1. Go to the URL and login with Editor. 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 3. Dashboard 4. Click Settings. 5. Click Security Settings. | Fine Tuning | GUI Error | Low | Solved | Ridwan | [5 empty] | Amirul | Solved
TC_034 | Settings > Security settings |  | 2023-02-01 | Issue: There isn't any show password button in all text fields as per figma design STR: 1. Go to the URL and login with Editor. 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 3. Dashboard 4. Click Settings. 5. Click Security settings. | Fine Tuning | GUI Error | Low | Solved | Ridwan | [5 empty] | Amirul | Solved
TC_035 | File Report > Regions |  | 2023-02-01 | Issue: Region Box text color are not matching with Figma, color should be black. STR: 1. Go to the URL and login with Editor. 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 3. File Report > Region | Fine Tuning | GUI Error | Medium | Solved | Ridwan | [5 empty] | Amirul | Solved
TC_036 | File Report > Regions > Select Any Region |  | 2023-02-01 | Issue: There should be no Drop Down icon on 'Role' Because it is not changeable. STR: 1. Go to the URL and login with Creds. 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 3. Setting | Fine Tuning | GUI Error | Medium | Solved | Ridwan | [5 empty] | Amirul | Solved
TC_037 | Settings |  | 2023-02-01 | Issue: There is no back button as per Figma design. STR: 1. Go to the URL and login with Editor. 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 3. File Report > Region 4. Select Any Region. | CR | GUI Error | Low | Open | Ridwan | [5 empty] | Amirul | Solved
TC_038 | File Report > Regions > Click a card |  | 2023-01-31 | Issue: The table UI is not matched with Figm file. STR: 1. Go to the URL 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 3. Click File Report. 4. Click Regions. 5. Click a card. | Fine Tuning | GUI Error | Medium | Open | Ridwan | [5 empty] | Amirul | Solved
TC_039 | Settings |  | 2023-02-01 | Issue: There is no highlighting when Setting item are selected as per figma design. STR: 1. Go to the URL and login with Editor. 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 3. Setting | Fine Tuning | GUI Error | Medium | Solved | Ridwan | [5 empty] | Amirul | Solved
TC_040 | File Report > Regions > Click a card |  | 2023-01-31 | Issue: The table left-margin from menu bar is not matched with figma file. STR: 1. Go to the URL 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 3. Click File Report. 4. Click Regions. 5. Click a card. | Fine Tuning | GUI Error | Medium | Open | Ridwan |  | In the figma file the left-margin is 36px. |  |  |  | Amirul | Solved
TC_041 | Settings |  | 2023-02-01 | Issue: There should be no Title, only placeholder names on the Input Fields. (As per Figma Design) STR: 1. Go to the URL and login with Editor. 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 3. Setting 4. Select Any Setting | Fine Tuning | GUI Error | Medium | Solved | Ridwan | [5 empty] | Amirul | Solved
TC_042 | Settings |  | 2023-02-01 | Issue: No Eye Icon found on Password fields (as per Figma Design) STR: 1. Go to the URL and login with Editor. 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 3. Setting 4. Select Security | Fine Tuning | GUI Error | Medium | Solved | Ridwan | [5 empty] | Amirul | Solved
TC_043 | RapidPro |  | 2023-02-01 | Issue: Create flow button name should be Create new according to figma design. STR: 1. Go to the URL and login with Editor. 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 3. Dashboard 4. Click RapidPro. | Fine Tuning | GUI Error | Medium | Open | Ridwan |  | It should match design as per figma design. |  |  |  | Amirul | Solved
TC_044 | RapidPro |  | 2023-02-01 | Issue: After clicking RapidPro button, Dropdown symbol should change into Dropup symbol as per Figma design. STR: 1. Go to the URL and login with Editor. 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 3. Dashboard 4. Click RapidPro. | Fine Tuning | GUI Error | Medium | Open | Ridwan | [5 empty] | Amirul | Solved
TC_045 | RapidPro |  | 2023-02-01 | Issue: Create flow module is not matching as per figma design. STR: 1. Go to the URL and login with Editor. 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 3. Dashboard 4. Click RapidPro. 5. Add a new flow. | Fine Tuning | GUI Error | Medium | Open | Ridwan |  | It should match design as per figma design. |  |  |  | Amirul | Solved
TC_046 | RapidPro |  | 2023-02-01 | Issue: After creating a flow, Created flow design is not as per figma design. STR: 1. Go to the URL and login with Editor. 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 3. Dashboard 4. Click RapidPro. 5. Add a new flow. | Fine Tuning | GUI Error | Medium | Open | Ridwan |  | It should match design as per figma design. |  |  |  | Amirul | Solved
TC_047 | Login > User > Create Admin |  | 2023-02-01 | Issue: In the Add Admin, there is Title on the Input fields, but as per Figma, only placeholder text should exist. STR: 1. Go to the URL 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 3. Click USer. 4. Click Admin. 5. Click Add Admin. | Fine Tuning | GUI Error | Medium | Open | Ridwan | [5 empty] | Amirul | Not Solved
TC_048 | User > Editor |  | 2023-01-31 | Issue: Add Editor & Edit Editor UI is not matched with Figma File. STR: 1. Go to the URL 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 3. Click User 4. Click Add Editor. 5. Click Edit from table 3 dots. | Fine Tuning | GUI Error | Medium | Open | Ridwan | [5 empty] | Amirul | Solved
TC_049 | File Report > Regions > Click a card |  | 2023-01-31 | Issue: The table UI is not matched with Figma file. STR: 1. Go to the URL 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 3. Click File Report. 4. Click Regions. 5. Click a card. | Fine Tuning | GUI Error | Medium | Open | Ridwan
TC_050 | File Report > Regions > Click a card |  | 2023-01-31 | Issue: The table left-margin from menu bar is not matched with figma file. STR: 1. Go to the URL 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 3. Click File Report. 4. Click Regions. 5. Click a card. | Fine Tuning | GUI Error | Medium | Open | Ridwan |  | In the figma file the left-margin is 36px.
TC_051 | User > Editor |  | 2023-01-31 | Issue: Add Editor & Edit Editor UI is not matched with Figma File. STR: 1. Go to the URL 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 3. Click User 4. Click Add Editor. 5. Click Edit from table 3 dots. | Fine Tuning | GUI Error | Medium | Open | Ridwan
TC_052 | Rapid Pro > Flow List |  | 2023-01-31 | Issue: Whole page UI is not matched with Figma. STR: 1. Go to the URL 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 3. Click Eapid Pro 4. Click Flow List. | Fine Tuning | GUI Error | High | Open | Ridwan |  | Should follow the Figma Design properly. |  |  |  | Amirul | Solved
TC_053 | File Report > Rapid Pro |  | 2023-02-01 | Issue: Expand function on File Report > RapidPro is not matched with Figma STR: 1. Go to the URL 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 3. Click File Report 4. Click rapidPro | Fine Tuning | GUI Error | Low | Open | Ridwan | [5 empty] | Amirul | Not Solved
TC_054 | Create Flow > Add Question |  | 2023-02-01 | Issue: Add Question Windows has extra space below. STR: 1. Go to the URL 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 3. Click Rapid Pro 4. Create Flow 5. Add Question | Fine Tuning | GUI Error | Low | Open | Ridwan | [5 empty] | Amirul | Not Solved
TC_055 | Create Flow |  | 2023-02-01 | Issue: Create Flow Description Box is smaller when trying to edit. STR: 1. Go to the URL 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 3. Click Rapid Pro 4. Create Flow | Fine Tuning | GUI Error | Low | Open | Ridwan | [5 empty] | Amirul | Not Solved
TC_056 | RapidPro |  | 2023-02-08 | Issue: Create flow button and Flow List button is not perfectly alligned. STR: 1. Go to the URL and login with Editor. 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 3. Dashboard 4. Click RapidPro. | Fine Tuning | GUI Error | Low | Open | Ridwan
TC_057 | Dashboard |  | 2023-02-08 | Issue: In Dashboard, All dropdown symbols beside module names are placed slightly upper. All symbols should've placed perfectly. STR: 1. Go to the URL and login with Editor. 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 3. Dashboard | Fine Tuning | GUI Error | Low | Open | Ridwan
TC_058 | File Report > IOGT |  | 2023-02-08 | Issue: In File Report, the name of IOGT is spelled miscorretly. It should've wrote down "IoGT" according to figma design STR: 1. Go to the URL and login with Editor. 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 3. Dashboard | Fine Tuning | GUI Error | Low | Open | Ridwan
TC_059 | Settings |  | 2023-02-08 | Issue: Partition part in all security field is not required (as per Figma Design) STR: 1. Go to the URL and login with Editor. 2. Use the credential to login: email: superadmin@ucms.com password: 12345678 3. Setting 4. Select Security | CR | GUI Error | Low | Decision Pending | Ridwan
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425